## ProductBacklog
HRMS BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Employee | Register Myself Using Company Mail Id | I Can Receive A Confirmation/Verification Mail | 1
1 | SB1/US2 | Employee | Receive A Confirmation Mail | I Can Access The Digital Company System | 1
1 | SB1/US3 | Employee | Login Into The System Using Comapany Mail Id And Password | I Can View/Edit My Profile | 1
|  | Employee | Check the no.of leaves left | I can check my leaves. | 3
1 | SB1/US4 | Employee | View The Leave History | I Can See The Salary based on working days | 3
|  | Employee | Check earned leaves | I Can check earned leaves. | 3
|  | Employee | Check medical leaves | I Can check medical leaves | 3
1 | SB1/US5 | Employee | View The Employee Resource Center(ERC) | I Can Work According To The ERC | 1
|  | Employee | View The Attendance | I Can be on Time | 2
| SB1/US7 | Employee | Modify The Account Password | I Can Keep My Account Secure | 1
|  | Employee | View My Work Allocation Report | I Can be on Time | 2
|  | Employee | See The Fees Status | I Can have The Fees On/Before Time | 2
|  | Employee | Apply for Leaves | I Can plan for further | 1
|  | Employee | See My Travel Claim(If any) | I Can Have Required Information | 2
|  | Employee | Fill local outstation travel claim form | I Can check my claim | 1
|  | Employee | Fill local Conveyance claim form | I Can check my claim | 1
|  | Employee | Check the Bonus Details | I can check my bonus given. | 2
|  | Employee | Check salary details. | I Can check my salary details. | 2
|  | Employee | Download Payroll | I Can take it as reference | 3
|  | Employee | Download Logo | I Can download logo of company. | 1
|  | Employee | Employee Grievances | I Can share my problems | 1
|  | Employee | Post a Complaint | I Can write the complaint. | 1
|  | Employee | Check List of holidays | I can check the list of holidays. | 1
|  | Employee | View the internal notices. | I can check the notices/Circulars. | 1
|  | Employee | Check Seniority list | I can view seniority list as per date of joining. | 1
|  | Employee | View the Colleague Details | I can check colleagues details(no personal details) | 2
|  | DBA | Fire Insert Queries | I Can Insert New Records In The Database | 2
|  | DBA | Fire Select Queries | I Can View The Records | 2
|  | DBA | Fire Update Queries | I Can Keep The Database Updated | 2
|  | DBA | Changes in the scheme | I Can Access The Human resource management system | 2
|  | DBA | Fire Delete Queries | I Can Remove Unwanted Or Faulty Data | 2
|  | DBA | Take Backup | I Can Save The Old Records In The Database For Future Use | 2
|  | DBA | Delete Backup | I Can Delete The Records Which Is Not Needed Any More | 2
|  | HR | Login Into The System Using Social Logins | I Can Access The Human resource management system | 1
|  | HR | Modify The Account Password | I Can Keep My Account Secure | 1
|  | HR | Create Employee Accounts | Employee can be register. | 1
|  | HR | Check status for the Work To The Employees. | Work Can Be Done. | 3
|  | HR | Check The Work Report | Can download and check | 3
|  | HR | Allot The Work To The Employees. | Work Can Be Done. | 3
|  | HR | View The Attendance Of employees | I Can Know The employee Strength In The office. | 3
|  | HR | Edit number of leave application. | I Can edit how many leave does employee can take. | 3
|  | HR | View The Result List Of The Students | I Can Monitor The Performance Of The Students | 3
|  | HR | Check the leave application | I Can accept or reject leave application from employees. | 2
|  | HR | View the holidays | I Can Give information about holidays to employees. | 1
|  | HR | View The List Of Celebrations | I Can Plan Activities For The Celebration | 1
|  | HR | Edit employees | I can able to edit information of employees | 3
|  | HR | Add holidays | I Can Give information about holidays to employees. | 3
|  | HR | Calculate salary of employee | I can able to calcuate salary | 3
|  | HR | View Employee Detaills | I can able to check information of employees | 2
|  | HR | Send notice | I Can Pass On Important Information | 2
|  | HR | Check salary details. | I Can Review | 2
|  | HR | Create Notices | I Can Pass On Important Information | 1
|  | HR | Allocate and change the Travels | Transport respectives | 3
|  | HR | Can Check for the Travels | Transport respectives | 2
|  | HR | View Notices | I Can Review Or Read New Notices | 1
|  | HR | Reject leave application | I Can accept or reject leave application from employees. | 3
|  | HR | have Messages from Employees | They Can Be Informed by the employee | 3
|  | HR | Send Messages To Employees | They Can Be Informed For An Event | 2

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | Register Myself Using Company Mail Id | SB1/D1/T1 | Designing of GUI
|  | SB1/D1/T2 | Validating user input at client level
|  | SB1/D1/T3 | Validating user input at server level
|  | SB1/D1/T4 | Connection with Database to insert the record.
|  | SB1/D1/T5 | Testing of the module on localhost and then on server.
SB1/US2 | Receive A Confirmation Mail | SB1/D2/T1 | Designing of Email(to be send)
|  | SB1/D2/T2 | Send Email via coding using the Mandrill App
|  | SB1/D2/T3 | Connection with database to update the status in the database.
|  | SB1/D2/T4 | Testing of the module on localhost and then on server.
SB1/US3 | Login Into The System Using Comapany Mail Id And Password | SB1/D3/T1 | Designing of GUI
|  | SB1/D3/T2 | Validating user input at client level
|  | SB1/D3/T3 | Validating user input at server level
|  | SB1/D3/T4 | Connection with Database to insert the record.
|  | SB1/D3/T5 | Testing of the module on localhost and then on server.
SB1/US6 | Login Into The System Using Social Logins | SB1/D4/T1 | Designing of GUI
|  | SB1/D4/T2 | Validating user input at client level
|  | SB1/D4/T3 | Validating user input at server level
|  | SB1/D4/T4 | Connection with Database to insert the record.
|  | SB1/D4/T5 | Testing of the module on localhost and then on server.
SB1/US7 | Modify The Account Password | SB1/D5/T1 | Designing of GUI
|  | SB1/D5/T2 | Validating user input at client level
|  | SB1/D5/T3 | Validating user input at server level
|  | SB1/D5/T4 | Connection with Database to insert the record.
SB1/US27 | View The Employee Resource Center(ERC) | SB1/D6/T1 | Designing of GUI
|  | SB1/D6/T2 | Validating user input at client level
|  | SB1/D6/T3 | Validating user input at server level
|  | SB1/D6/T4 | Connection with Database to insert the record.
|  | SB1/D6/T5 | Testing of the module on localhost and then on server.
SB1/US27 | Fill local outstation travel claim form | SB1/D7/T1 | Designing of GUI
|  | SB1/D7/T2 | Validating user input at client level
|  | SB1/D7/T3 | Validating user input at server level
|  | SB1/D7/T4 | Connection with Database to insert the record.
|  | SB1/D7/T5 | Testing of the module on localhost and then on server.
SB1/US150 | Fill local Conveyance claim form | SB1/D8/T1 | Designing of GUI
|  | SB1/D8/T1 | Validating user input at client level
|  | SB1/D8/T2 | Validating user input at server level
|  | SB1/D8/T3 | Connection with Database to insert the record.
|  | SB1/D8/T4 | Testing of the module on localhost and then on server.
SB1/US28 | Download Logo | SB1/D9/T1 | Designing of GUI
|  | SB1/D9/T2 | Validating user input at client level
|  | SB1/D9/T3 | Validating user input at server level
|  | SB1/D9/T4 | Connection with Database to insert the record.
|  | SB1/D9/T5 | Testing of the module on localhost and then on server.
SB1/US50 | Employee Grievances | SB1/D10/T1 | Designing of GUI
|  | SB1/D10/T2 | Validating user input at client level
|  | SB1/D10/T3 | Validating user input at server level
|  | SB1/D10/T4 | Connection with Database to insert the record.
|  | SB1/D10/T5 | Testing of the module on localhost and then on server.
SB1/US53 | Post a Complaint | SB1/D11/T1 | Designing of GUI
|  | SB1/D11/T2 | Validating user input at client level
|  | SB1/D11/T3 | Validating user input at server level
|  | SB1/D11/T4 | Connection with Database to insert the record.
|  | SB1/D11/T5 | Testing of the module on localhost and then on server.
SB1/US55 | Check List of holidays | SB1/D12/T1 | Designing of GUI
|  | SB1/D12/T2 | Validating user input at client level
|  | SB1/D12/T3 | Validating user input at server level
|  | SB1/D12/T4 | Connection with Database to insert the record.
SB1/US51 | View the internal notices. | SB1/D13/T1 | Designing of GUI
|  | SB1/D13/T2 | Validating user input at client level
|  | SB1/D13/T3 | Validating user input at server level
|  | SB1/D13/T4 | Connection with Database to insert the record.
|  | SB1/D13/T5 | Testing of the module on localhost and then on server.
SB1/US70 | Check Seniority list | SB1/D14/T1 | Designing of GUI
|  | SB1/D14/T2 | Validating user input at client level
|  | SB1/D14/T3 | Validating user input at server level
|  | SB1/D14/T4 | Connection with Database to insert the record.
|  | SB1/D14/T5 | Testing of the module on localhost and then on server.
SB1/US71
SB1/US72

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2018-09-04 | 180 | 180 | Tasks
2018-09-12 | 120 | 140
2018-09-11 | 80 | 110
2018-09-14 | 56 | 110
2018-09-16 | 15 | 80
2018-09-18 | 5 | 20
Days

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
| Add Department | SB2/D1/T1 | Designing the GUI | SP
|  | SB2/D1/T2 | Connection with database to fetch the data | RA
|  | SB2/D1/T3 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TA into the application(using poornima email account) | SB2/D2/T1 | Designing of GUI | PB
|  | SB2/D2/T2 | Validating user input at client level | RM
|  | SB2/D2/T3 | Validating user input at server level | SP
|  | SB2/D2/T4 | Connection with Database to insert the record. | RA
|  | SB2/D2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TA Receiving Confirmation Email | SB2/D3/T1 | Designing of Email(to be send) | PB
|  | SB2/D3/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D3/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D3/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register TO into the application(using poornima email account) | SB2/D4/T1 | Designing of GUI | PB
|  | SB2/D4/T2 | Validating user input at client level | RM
|  | SB2/D4/T3 | Validating user input at server level | SP
|  | SB2/D4/T4 | Connection with Database to insert the record. | RA
|  | SB2/D4/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| TO Receiving Confirmation Email | SB2/D5/T1 | Designing of Email(to be send) | PB
|  | SB2/D5/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D5/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D5/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Add Subject | SB2/D6/T1 | Designing of GUI | PB
|  | SB2/D6/T2 | Validating user input at client level | RM
|  | SB2/D6/T3 | Validating user input at server level | SP
|  | SB2/D6/T4 | Connection with Database to insert the record. | RA
|  | SB2/D6/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Register Timetable Co-ordinator into the application | SB2/D7/T1 | Designing of GUI | PB
|  | SB2/D7/T2 | Validating user input at client level | RM
|  | SB2/D7/T3 | Validating user input at server level | SP
|  | SB2/D7/T4 | Connection with Database to insert the record. | RA
|  | SB2/D7/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM
| Timetable Co-ordinator Receiving Confirmation Email | SB2/D8/T1 | Designing of Email(to be send) | PB
|  | SB2/D8/T2 | Send Email via coding using the Mandrill App | SP
|  | SB2/D8/T3 | Connection with database to update the status in the database. | RA
|  | SB2/D8/T4 | Testing of the module on localhost and then on server. | RA+SP+PB+RM

## SB Hours 02
Sprint Backlog 2
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch02
Spring Backlog 02 burn down chart
Date | Planned Total Task | Actual Uncompleted Task
2017-09-25 | 177 | 177 | Tasks
2017-09-28 | 110 | 177
2017-10-02 | 80 | 177
2017-10-05 | 66 | 177
2017-10-07 | 15 | 177
2017-10-09 | 5 | 177
0
Days

## SprintBacklog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>

## SB Hours 03
Sprint Backlog 3
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch03
Spring backlog 3 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2018-10-16 | 120 | 120 | Tasks
2018-10-18 | 110 | 120
2018-10-20 | 80 | 120
2018-10-21 | 25 | 120
2018-10-22 | 15 | 120
2018-10-23 | 0 | 120
0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB Hours 04
Sprint Backlog 4
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2019-01-10 | 190 | 190 | Tasks
2019-01-11 | 110 | 190
2019-01-12 | 80 | 190
2019-01-13 | 25 | 190
2019-01-14 | 15 | 190
2019-01-15 | 0 | 190
0
Days